## Sheet1
Iteration 1, 3 wks 5/17/21 - 6/11/21 | Iteration 2, 2 wks 6/14/21 - 6/25/21 | Iteration 3, 2 wks 6/28/21 - 7/9/21 | Iteration 4, 2 wks 7/12/21 - 7/23/21 | Iteration 5, 2 wks 7/26/21 - 8/6/21
UC01: Do One points: 4 priority: 1 depends on: None | UC02: Do Two points: 3 priority: 2 depends on: UC01 | UC05: Do Five points: 3 priority: 2 depends on : UC04 | UC07: Do Seven points: 3 priority: 3 depends on: UC03, UC06 | UC09: Do Nine points: 3 priority: 2 depends on: UC03
UC03: Do Three points: 4 priority: 1 depends on: None | UC04: Do Four points: 3 priority: 1 depends on: None | UC06: Do Six points: 3 priority: 2 depends on: UC03 | UC08: Do Eight points: 3 priority: 2 depends on: UC03