## riskManagement
| RISK | RESOLUTION | JUSTIFICATION
1 | unrealistic schedules and budgets | detailed schedule estimation, design to cost, incremental development, software reuse, requirements scrubbing | Being unable to deliver the product on time and on budget must be a primary concern for the development effort.
2 | personnel shortfalls | cross training | Because the development team is small, it should be possible to cross train to mitigate the risk of a loss of personnel.
3 | continuing stream of requirements changes | high change threshold, information hiding, incremental development (deferring changes to later increments) | The project must be prepared to change course do to changes in the requirements as each iteration is completed.
4 | SQL injection | Using parameterized statements and other language features to protect against SQL injection attacks | Because our system uses a database to persist information, it must be protected from an SQL injection attack, which is a common attack on this type of system.
5 | Cross site scripting | Filtering input, using appropriate response headers, and other language features to detect and prevent cross site scripting (XSS) attacks | Because our system is web-based, it is susceptible to cross site scripting attacks. This vulnerability must be addressed with countermeasures.